# 1

|  |
| --- |
| **Name: Raneem Sadeh** |
| **Project Title: Challenges and opportunities of Big Data 6 V’s in modern** |
| **Date: 27/7/2024** |
| **Update on weekly research/tasks achieved**  **Points to consider:**  What have you completed?   * I have completed the Introduction research. * I found an organization for my research. * Drafted and sent a collaboration request to Zakaria from Tourstify.   Did you fulfil task requirements?   * Partially. I completed the literature review and secured a collaboration with Tourstify, but I still need to gather detailed information on Tourstify’s use of big data technologies.   Are you on track and within deadlines set?   * While I am on track with some tasks, the detailed study on Tourstify’s big data tools and technologies is still pending.   Did you need to make any changes to your project management plan?   * Yes, I may need to adjust the timeline for gathering detailed information from Tourstify. |
| **Any risks and/or issues identified?**  **Points to consider:**  Did you identify risks/issues with a lack of skills required for undertaking research/tasks?   * Identified the need for advanced research skills for the next phase of the project. Plan to seek guidance to bridge this gap.   Did you identify any additional risks/issues that have an impact on the project management plan?   * Possible delay in obtaining detailed information from Tourstify. |
| **Problems encountered**  **Points to consider:**  What barriers did you face?   * There were delays in receiving responses from potential companies. * Difficulty in gathering detailed technical information from Tourstify.   How did you overcome them?   * Plan a follow-up meeting with Tourstify to gather the necessary information. |
| **New ideas and change of project direction** |
| **What have I learnt about myself this week?**  **Points to consider:**  How did I feel when I had to deal with tasks/problems?   * Alittle bit stress, but I manage to stay focused.   Did I find it useful to complete the tasks?   * Sure, from this task I have learned a lot, from how to make good research to how to communicate with companies and deal with them.   How well have I performed? What did I contribute?   * I performed well by meeting initial deadlines.   What can I improve on next week?   * I would improve every skill I had use in this task for the next time.   How might this learning apply in the future? |
| **Tasks planned for next week**  **Points to consider:**  Which tasks are priority?   * Conduct a detailed study on Tourstify’s big data tools and technologies. * Begin collecting and analyzing primary data from Tourstify.   Have you set aside sufficient time for completion?   * Yes, I had a well plan to complete to finish every task in it’s time. |
| **Project plan status to date ( on, ahead, behind): Partially on track** |
| **Supervisor comments to address** |
|  |

# 2

|  |
| --- |
| **Name: Raneem Sa’deh** |
| **Project Title: Tourstify** |
| **Date: 10 / 08 / 2024** |
| **Update on weekly research/tasks achieved**  **Points to consider:**  What have you completed?   * Attended events about Big Data. * Visited companies, including Tourstify, to observe how they utilize Big Data.   Did you fulfil task requirements?   * Yes, I aimed to deepen my understanding of Big Data and its application in companies, which was successfully achieved.   Are you on track and within deadlines set?   * Yes, I am on track with the learning goals **I** set for this week.   Did you need to make any changes to your project management plan?   * No |
| **Any risks and/or issues identified?**  **Points to consider:**  Did you identify risks/issues with a lack of skills required for undertaking research/tasks?   * Not that issues, its only that it was hard to find events for Big Data.   Did you identify any additional risks/issues that have an impact on the project management plan? - No |
| **Problems encountered**  **Points to consider:**  What barriers did you face? – There is NO barriers this week.  How did you overcome them? -N/A |
| **New ideas and change of project direction - NO** |
| **What have I learnt about myself this week?**  **Points to consider:**  How did I feel when I had to deal with tasks/problems?   * I felt motivated to learn more about Big Data   Did I find it useful to complete the tasks?   * Yes, the tasks were very useful in building my understanding.   How well have I performed? What did I contribute?   * I performed well, actively participating in events and company visits to gather valuable insights.   What can I improve on next week?   * Applying what I learned in the technical report.   How might this learning apply in the future?   * It will be crucial when addressing Big Data challenges and opportunities in the project. |
| **Tasks planned for next week**  **Points to consider:**  Which tasks are priority?   * Complete working on the technical report, utilizing the insights gained this week. * Analyze the specific challenges companies face with Big Data.   Have you set aside sufficient time for completion?  Yes, I have allocated time. |
| **Project plan status to date ( on, ahead, behind): On track** |
| **Supervisor comments to address** |
|  |

# **3**

|  |
| --- |
| **Name:Raneem Sa’deh** |
| **Project Title: Tourstify** |
| **Date: 16/08/2024** |
| **Update on weekly research/tasks achieved**  **Points to consider:**  What have you completed?  This week, I focused on researching several key areas essential to our project. I explord the features and opereational areas of Tourstify, identified both internal and external stakeholders, and analyzed how these stakeholders impact the companys' goals. Additionally, I delved into the challenges that could hinder the success of the organizations business. I also reviewed three main methods that could be employed in changing parallel running processes. Finaly, I expanded my knowledge of both qualitative and quantitative research approaches.  Did you fulfil task requirements?  Yes, I have met the requirements of the tasks outlined for this week, but there is a little mistings.  Are you on track and within deadlines set?  Yes, I am inshallah on track and within the deadlines set.  Did you need to make any changes to your project management plan?  No changes to the project management plan were necessary this week. |
| **Any risks and/or issues identified?**    **Points to consider:**  Did you identify risks/issues with a lack of skills required for undertaking research/tasks?  Did you identify any additional risks/issues that have an impact on the project management plan?  I didnot encounter any significant risks or issues that could impact the project managment plan. However, I recognize the need to continue developing skills in analyzing complex businesss challenges and stakeholder management. |
| **Problems encountered**  **Points to consider:**  What barriers did you face? I faced some difficulty in understanding the implications of certain qualitative and quantitative methods and how they can be applied to our project.  How did you overcome them? To overcome this, I spent additional time reading up on these methods and discussing them with peers to gain better clarity. |
| **New ideas and change of project direction**  **No new ideas or significant changes in project direction were identified this week.** |
| **What have I learnt about myself this week?**    **Points to consider:**  How did I feel when I had to deal with tasks/problems?  Did I find it useful to complete the tasks?  How well have I performed? What did I contribute?  I found the tasks challenging yet rewarding, and they have helped me improve my research and analytical skills. I am performing well and contributing meaningful insights to the project. However, I need to work on improving my ability to synthesize complex information more efficiently.  What can I improve on next week?  How might this learning apply in the future?  This experience has taught me the value of persistence and continuous learning. Moving forward, I will allocate more time to areas where I lack confidence, ensuring I am better prepared to tackle similar challenges in the future. |
| **Tasks planned for next week**  **Points to consider:**  Which tasks are priority?  Begin drafting a report on the challenges facing Tourstify and possible solutions.  Further explore qualitative and quantitative methods and their application in the project.  Have you set aside sufficient time for completion?  I have set aside sufficient time to complete these tasks by the end of next week. |
| **Project plan status to date ( on, ahead, behind): On track** |
| **Supervisor comments to address** |
|  |

# 4

|  |
| --- |
| **Name: Raneem Sadeh** |
| **Project Title: Tourstify** |
| **Date: 24/08/2024** |
| **Update on weekly research/tasks achieved**  **Points to consider:**  What have you completed?   * I completed the entire interview with the AI engineer and transcribed it. * Wrote the business requirements for the project. * Started the project management plan and completed significant portions of it.   Did you fulfil task requirements?   * Yes, I fulfilled the requirements for both the interview and the initial parts of the project management plan.   Are you on track and within deadlines set?   * Yes, I am on track to meet the deadlines and I know that I could complete the remaining tasks on time.   Did you need to make any changes to your project management plan?   * No |
| **Any risks and/or issues identified?**  **Points to consider:**  Did you identify risks/issues with a lack of skills required for undertaking research/tasks?   * No   Did you identify any additional risks/issues that have an impact on the project management plan?   * No |
| **Problems encountered**  **Points to consider:**  What barriers did you face?   * The only barrier was ensuring the accuracy of the interview transcription.   How did you overcome them?   * By carefully reviewing the transcription multiple times. |
| **New ideas and change of project direction**   * At this stage, no new ideas have been implemented. |
| **What have I learnt about myself this week?**  **Points to consider:**  How did I feel when I had to deal with tasks/problems?   * Managing the interview and transcription process was particularly satisfying, so I fell that I’m organized when dealing with them.   Did I find it useful to complete the tasks?   * Yes, completing these tasks has been useful in advancing the project   How well have I performed? What did I contribute?   * I believe I have performed well this week, contributing effectively to the project's progress by completing important tasks.   What can I improve on next week?   * To enhance my performance next week, I will allocate time more precisely to efficiently complete the remaining parts of the project management plan.   How might this learning apply in the future?   * It has reinforced the importance of staying organized in managing project tasks. |
| **Tasks planned for next week**  **Points to consider:**  Which tasks are priority?   * Finalizing the project management plan. * Reviewing and refining the business requirements document.   Have you set aside sufficient time for completion?   * I have allocated sufficient time to complete these tasks |
| **Project plan status to date ( on, ahead, behind): On track** |
| **Supervisor comments to address** |
|  |

# 5

|  |
| --- |
| **Name: Raneem Sadeh** |
| **Project Title: Tourstify** |
| **Date: 31/8/2024** |
| **Update on weekly research/tasks achieved**  This week i finised a bunch of tasks. First, i complet the scope managemnt, and also creat the gantt chart for the project. I also work on the Critical Path Analysis by find the tasks that is most importent for the project deadline. For Cost Estimate, I follow four steps in project cost mangement to make a budget. I wrote a Change Management Plan for how the company will use the new big data system, and made sure people know about the changes, get ready, and stay strong after the changes go live. Finally, I created a Probability Impact Matrix to see what risks might happen and how bad they can be.  **Points to consider:**  What have you completed?   * Scope management, Gantt chart, Critical Path Analysis, Cost Estimate, Change Management Plan, Probability Impact Matrix   Did you fulfil task requirements?   * Yes, all tasks are done as needed.   Are you on track and within deadlines set?   * Yup, I’m on track and think I'll finish everything on time   Did you need to make any changes to your project management plan?   * Nope |
| **Any risks and/or issues identified?**  **Points to consider:**  Did you identify risks/issues with a lack of skills required for undertaking research/tasks?   * Not really   Did you identify any additional risks/issues that have an impact on the project management plan?   * No |
| **Problems encountered**  **Points to consider:**  What barriers did you face?  I didn’t face any big problems this week also.  How did you overcome them?   * Didn’t need to overcome anything big |
| **New ideas and change of project direction**   * **NO** |
| **What have I learnt about myself this week?**  **Points to consider:**  How did I feel when I had to deal with tasks/problems?   * I felt pretty good, no any stress this week.   Did I find it useful to complete the tasks?   * Yes, doing these tasks was helpful and I learned more about project management.   How well have I performed? What did I contribute?   * I did well, got a lot done.   What can I improve on next week?   * Maybe focus on the details a bit more and complete the next tasks such as the presentation and the evaluate   How might this learning apply in the future?   * It will help me with planning and managing future projects better |
| **Tasks planned for next week**  **Points to consider:**  Which tasks are priority?   * Finish the remaining parts of the project plan the presentation and the evaluate   Have you set aside sufficient time for completion?  Yes, I made sure there’s enough time to get everything done |
| **Project plan status to date ( on, ahead, behind): On track** |
| **Supervisor comments to address** |
|  |

# 6

|  |
| --- |
| **Name: Raneem Yahya Sadeh** |
| **Project Title: Tourstify Matching technique using AI** |
| **Date: 4/9/2024** |
| **Update on weekly research/tasks achieved**  **Points to consider:**  What have you completed?  - **Software Development Methodology:** I chose a method for the project and explained it in detail.  - **Stakeholder Communication Plan:** I found out who the stakeholders are and planned how to communicate with them. I filled in the table in the project management plan (PMP).  - **Planning Decisions:** I gave reasons for the key planning choices, like costs, deliverables, and the chosen method.  - **Project Recommendations:** I reviewed the recommendations and explained the budget, timeline, risks, and resources.  - **Performance Review:** I talked about how accurate the research was and checked if the project recommendations fit the organization's needs.  Did you fulfil task requirements?   * Yes, I completed all the tasks required, including choosing a method, planning communication, making decisions, and reviewing performance.   Are you on track and within deadlines set?   * Yes, the project is on track and all parts are finished on time.   Did you need to make any changes to your project management plan?   * Yes, I made changes to how we communicate, adjusted the budget and timeline, and improved the change management plan to help the project succeed. |
| **Any risks and/or issues identified?**  **Points to consider:**  Did you identify risks/issues with a lack of skills required for undertaking research/tasks?   * Yes, I noticed some risks because the team lacked certain technical skills. To fix this, I set up extra training and brought in outside experts to help.   Did you identify any additional risks/issues that have an impact on the project management plan?   * Yes, I also found risks with resource availability and tight deadlines. I updated the project plan, moved resources around, and made better backup plans to deal with possible delays. |
| **Problems encountered**  **Points to consider:**  What barriers did you face?   * I faced problems like missing technical skills in the team and issues with resources and deadlines.   How did you overcome them?   * To fix these, I organized training sessions for the team, hired outside help, adjusted the timeline, and made stronger backup plans to handle delays. |
| **New ideas and change of project direction** |
| **What have I learnt about myself this week?**  **Points to consider:**  How did I feel when I had to deal with tasks/problems?   * I felt challenged but motivated when dealing with tasks and problems. Even though it was tough, I was driven to find solutions and keep the project on track.   Did I find it useful to complete the tasks?   * Yes, completing the tasks was very useful. It helped me improve my project management skills, boost the team’s abilities, and keep the project moving forward.   How well have I performed? What did I contribute?   * I think I did well, making good decisions, solving problems, and keeping communication clear with everyone involved.   What can I improve on next week?   * Next week, I can get better by spotting problems earlier, improving risk management, and communicating more proactively with the team.   How might this learning apply in the future?   * What I learned will help in future projects by making me better at managing risks, using resources wisely, and handling unexpected issues, leading to smoother project management. |
| **Tasks planned for next week**  **Points to consider:**  Which tasks are priority?   * The main tasks are finalizing the communication plan, checking recommendations, and dealing with any remaining risks in the project plan.   Have you set aside sufficient time for completion?   * Yes, I have set aside enough time to finish these important tasks and included extra time to deal with any unexpected issues. |
| **Project plan status to date ( on, ahead, behind): On Track** |
| **Supervisor comments to address** |
|  |